## TestPlan
Test Planner and Tracker |  |  | Team 5
Test No. ID | Related Use case | Pre-conditions | Test Description (steps) | Expected Outcome | Sprint 2 Outcome (color code cell background) | Comments (if test case failed) | Sprint 3 Outcome (color code cell background) | Comments (if test case failed) | Sprint 4 Outcome (color code cell background) | Comments (if test case failed) | R1 Outcome (color code cell background) | Comments (if test case failed) | Sprint 5 Outcome (color code cell background) | Comments (if test case failed) | Sprint 6 Outcome (color code cell background) | Comments (if test case failed) | Sprint 7 Outcome (color code cell background) | Comments (if test case failed) | Sprint 8 Outcome (color code cell background) | Comments (if test case failed) | R2 Outcome (color code cell background) | Comments (if test case failed)
1 | Connection to bacnet | on same network | Connect to Lan of 4th floor to connect to bacnet | Connection to BACNET should be established. |  | not started |  | Learrning required bacnet language
2 | Control AC (of one AC) | on same network as the server | Connect to either lan or wifi network | AC temperature and state should be able to be controlled remotely. |  | not started |  | Learrning required bacnet language
3 | Login/Logout | Database and backend working | Type in the credentials | successful Login/logout. |  | not started |  | not completed yet
4 | History of AC usage | Database prepared to store AC usage | Go to view page and check if data is visible | Required data should be visible on app. |  | not started |  | Data gathering was required for BACNET
5 | Adjusting Temp | Connection with server | Change Temp from UI | AC temperature should be changed. |  | not started |  | bacnet required to adjust aTemp
6 | UI | frontend needs to be running | Check if the UI is responsive | UI should be responsive. |  | not started
7 | View | connection to backend must be present | 1. Go to the home page of the dashboard 2. Change graph plot | Graph of AC data should be rendered. |  | not started |  | not started |  | Required establishing hobolink connection |  | not started
8 | Hobolink connection | hobolink script must be run and connection must be present | Run the hobolink script | Hobolink data should be fetched. |  | not started |  | not started |  | not started |  | not started
9 | AC control through map | backend and frontend should be running, and connection to network must be present | Select AC through map, and set the temperature | AC should be set to assigned temperature. |  | not started |  | not started |  | not started |  | not started |  | Mapping was partially complete
10 | Request AC control to admin | app should be running, and control permission should not be there | 1. Select an AC through the map (for which control permission is not there) 2. Request permission from Admin | Admin should get alert from user. |  | not started |  | not started |  | not started |  | not started |  | not started
11 | Give AC control access to space user | app should be running, and admin should be logged in | Grant access request to user | Access should be granted to space user. |  | not started |  | not started |  | not started |  | not started |  | not started
12 | social media authentication | app should be running | Login using social media account | User should be logged in and new user should be created in the database. |  | not started |  | not started |  | not started |  | not started |  | not started |  | not started
13 | email alert | app should be running, email should be linked to app account | 1. login using email 2. send email alert to user through app | User should receive a mail from the app about overuse of AC. |  | not started |  | not started |  | not started |  | not started |  | not started |  | not started

## Instructions
Test plan Instructions
It is particularly important that you create a substantial set of Acceptance
Tests. These are tests based on the requirements document. Each acceptance
test should describe an operation to be performed by the user, and the
expected outcomes from that operation. The objective is to define a
comprehensive set of tests that between them cover all the features in the
requirements document. The tests should preferably cover all the frequent
"normal use" scenarios, as well as commonly occurring exception scenarios.
Each acceptance test must be described as a set of user instructions for
performing the test, much like a user manual. The outcomes description
specifies how the user knows whether the test succeeded or failed. The
reason for defining acceptance tests early in the life-cycle is to
facilitate "test-driven development". Developers can look at the acceptance
tests that their module must satisfy, and thereby know exactly what behavior
is expected from their module. Make sure to update these if/when
requirements change. Make sure to follow the suggested format.